## Introduction
Capstone Project Title | AUTOMATIC TICKET ASSIGNMENT
Description | AI techniques can classify incidents to right functional groups and help organizations reduce the resolving time of the issue and can focus on more productive tasks.
Members | Anand Kamal Praveen Priya Rama Vaibhav Vinayak | anand.sethurathinam@gmail.com kamalraj.m@gmail.com pgalav@gmail.com ancpriya73@gmail.com ramag80@gmail.com vaibhavkulkarni9@gmail.com vinayak.kudva@gmail.com

## Task List
Milestone 1 | Tasks | Presenter | Target
| 1. Problem interpretation |  | 2020-04-04
| - Understand the data |  | 2020-04-04
| - Make an abstract or an overview based on your approach |  | 2020-04-04
| - Break the problem into smaller tasks |  | 2020-04-04
| - Discuss among your teammates and share responsibilities |  | 2020-04-04
| 2. Data analysis and preprocessing: Visual displays are powerful when used well, so think carefully about the information the display. |  | 2020-04-11
| - Include any insightful visualization |  | 2020-04-11
| - Share and explain particularly meaningful features, interactions or summary of data |  | 2020-04-11
| - Display examples to input in your model |  | 2020-04-11
| - Explain changes to be incorporated into data so that it becomes ready for the model |  | 2020-04-11
| 3. Modeling |  | 2020-04-18
| - What kind of neural network you have used and why? |  | 2020-04-18
| - What progress you have made towards your intended solution? |  | 2020-04-18
Milestone 2
| 4. Model evaluation |  | 2020-04-25
| - Describe how you will proceed with the analysis |  | 2020-04-25
| - Compare different models and choose which model to use |  | 2020-04-25
| - Do hyper-parameter tuning of your model |  | 2020-04-25
| - How will you build on your initial analysis to increase the accuracy of your model? |  | 2020-04-25
| 5. Presentation and Report |  | 2020-05-09
| - You should start preparing the final report at least 2 weeks prior to the project completion date. |  | 2020-05-09
| - Teams should send a draft Last of the project before the last session to the mentor and get the necessary inputs for submission. |  | 2020-05-09
| - The expectations for the final report will be included in your Capstone course page. |  | 2020-05-09

## Communication plan
Day | Purpose | Time
Monday, Wednesday | 15 minute call - sync up | 8PM
Friday | Consolidation & Conclusion on what to present | 8PM
Saturday | Debrief post mentoring session | 11AM

## MOM
SI | Date | MOM Item | Type | Status | Owner | Next action
1 | 2020-04-01 | Shared Dir creation and adding members | Task | Closed | Vinayak | Shared Dir https://drive.google.com/open?id=1nxJAFHT8O76B2e0NvPhZNsdlhNyvp8Gb
2 | 2020-04-01 | Zoom scheduling for Monday Wednesday Friday (8 PM) Saturday (11 am) | Task | Open | Anand
3
4
5
6

## Open Issue List
Queries | Answer
1. single or consolidated file delivery?
2. report format
3. Should we give a weekly presentation ?
4. Should the presentation be for Individual or group single person ? is there a PPT template?
5. Are there 2 milestones or 3 milestones (different docs have different information)
6. Do we need 1 model or both classic model & nl model?